## Project Details
HSN Dropship Tool
Project Start Date | 2014-08-26
Project Completion Date | 2014-09-12
|  | Est. Time to Complete | Actual Time to Complete
Phase 1:
Setup Database |  | 0.5 Days
Generate Database Schema |  | 0.5 Days
Design User Interface |  | 0.5 Days
Phase 2:
Backend Coding |  | 7 Days
Connect C# to MySQL |  | 0.1 Days
Phase 3:
Testing |  | 2 Day
Phase 3:
After test modifications and testing |  | 3 Days

## Phase 1
|  | Incomplete | Complete |  |  |  | Phase 1:
ID | Phase 1 | Status |  | Notes | Est. Time to Complete | Actual Time to Complete | Setup Database | 0.5 Days
1a | Setup Database |  |  | Continuing to use the old dropship database. This way all DS tables are together. | 0.5 Days | 30 Mins. | Generate Database Schema | 0.5 Days
[7 empty] | Design User Interface | 0.5 Days
1b | Generate Database Schema |  |  | Copying the general PO structure of the raw file. | 0.5 Days | 0.5 Days |  |  | 1b. | hdr_user_defiend_field18 = Shipping Method
Added "ProcessedDate" column. If there is a "Date" entered here, then the query to process the Pos for daily shipments will skip this record.
1c | Design User Interface |  |  | Made a simple interface. The UI really doesn't really need too many features. | 0.5 Days | 0.5 Days

## Phase 2
|  | Incomplete | Complete |  |  |  | Phase 2:
ID | Phase 1 | Status |  | Notes | Est. Time to Complete | Actual Time to Complete | Backend Coding | 7 Days
2a | Backend Coding |  |  |  | 7 Days |  | Connect C# to MySQL | 1 Hour
2b | Connect C# to MySQL |  |  |  | 1 Hour